# Project:

Project Title:

Research Unit Logo Research Unit Name

N° Task

Duration

Start

End

2016, Semester 1

D J F M A M J

2016, Semester 2

J A S O N D

2017, Semester 3

J F M A

# 1 Session 1 Project Outline 84 days Fri 16-01-01 Wed 16-04-27

**04-13**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 2 |  | Success Plan | 1 day | Fri 16-01-01 | Fri 16-01-01 |
| 3 |  | Specific features | 1 day | Mon 16-01-04 | Mon 16-01-04 |
| 4 |  | Study Plan | 1 day | Tue 16-01-05 | Tue 16-01-05 |
| 5 |  | ÉTS Research Subject Identification Form | 1 day | Wed 16-01-06 | Wed 16-01-06 |
| 6 |  | Introduction | 10 days | Thu 16-01-07 | Wed 16-01-20 |
| 7 |  | Chapter 2: Literature Review | 20 days | Thu 16-01-21 | Wed 16-02-17 |
| 8 |  | Writing review paper | 30 days | Thu 16-02-18 | Wed 16-03-30 |
| 9 |  | Data collection | 5 days | Thu 16-03-31 | Wed 16-04-06 |
| 10 |  | Enrolment in XXX course | 5 days | Thu 16-04-07 | Wed 16-04-13 |
| 11 |  | Presentation 1 and quarterly evaluation | 1 day | Wed 16-04-13 | Wed 16-04-13 |
| 12 |  | Choice of suppliers | 5 days | Thu 16-04-14 | Wed 16-04-20 |
| 13 |  | Submitting review paper | 1 day | Wed 16-04-20 | Wed 16-04-20 |
| 14 |  | Holidays/Time off | 5 days | Thu 16-04-21 | Wed 16-04-27 |
| 15 |  |  |  |  |  |
| 16 |  | **Session 2 Literature Review** | **92 days** | **Thu 16-04-28** | **Fri 16-09-02** |
| 17 |  | Introduction | 2 days | Thu 16-04-28 | Fri 16-04-29 |
| 18 |  | Chapter 2: Literature Review | 10 days | Mon 16-05-02 | Fri 16-05-13 |
| 19 |  | Preliminary digital modelling | 15 days | Mon 16-05-16 | Fri 16-06-03 |
| 20 |  | Data collection | 10 days | Mon 16-06-06 | Fri 16-06-17 |
| 21 |  | Ordering materials | 5 days | Mon 16-06-20 | Fri 16-06-24 |
| 22 |  | DGA 1031 | 10 days | Mon 16-06-27 | Fri 16-07-08 |
| 23 |  | Presentation 2 and quarterly evaluation | 1 day | Fri 16-07-08 | Fri 16-07-08 |
| 24 |  | Writing scientific paper no. 1 | 5 days | Mon 16-07-11 | Fri 16-07-15 |
| 25 |  | Writing conference paper | 5 days | Mon 16-07-18 | Fri 16-07-22 |
| 26 |  | Submitting conference paper | 1 day | Fri 16-07-22 | Fri 16-07-22 |
| 27 |  | Assembly | 10 days | Mon 16-07-25 | Fri 16-08-05 |
| 28 |  | Holidays/Time off | 20 days | Mon 16-08-08 | Fri 16-09-02 |
| 29 |  |  |  |  |  |

**04-20**

**07-08**

**07-22**

File: PhD\_2016-02-02\_timeline\_model

Date: Tue 22-08-09

Task

Splitting

Milestone Summary

Project summary External tasks External milestones Idle task

Idle milestone

Idle summary

Manual task

Duration only

Manual summary delay Manual summary

Start only

End only Progress

Due date

**Research Student:** Research Student Name Page 1 of 4



|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Project:** Research Unit Logo Research Unit Name Project Title: | | | | | | | | | | | | | | | | | | | | | | |
| N° |  | Task | Duration | Start | End | D | 2016, Semester 1 | | | | | | 2016, Semester 2 | | | | | | 2017, Semester 3 | | | |
| J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A |
| 30 |  | **Session 3 Measurements** | **88 days** | **Mon 16-09-05** | **Wed 17-01-04** |  |  | | | | | |  | | | | | |  | | | |
| 31 |  | Chapter 2: Literature Review | 5 days | Mon 16-09-05 | Fri 16-09-09 |  | | | | | |  | | | |
| 32 |  | Assembly | 20 days | Mon 16-09-12 | Fri 16-10-07 |  | | | | | |  | | | |
| 33 |  | Calibration | 10 days | Mon 16-10-10 | Fri 16-10-21 |  | | | | | |  | | | |
| 34 |  | Data collection | 15 days | Mon 16-10-24 | Fri 16-11-11 |  | | | | | |  | | | |
| 35 |  | Enrolment in XXX course | 1 day | Mon 16-11-14 | Mon 16-11-14 |  | | | | | |  | | | |
| 36 |  | DGA 1032 | 20 days | Tue 16-11-15 | Mon 16-12-12 |  | | | | | |  | | | |
| 37 |  | Presentation 3 and quarterly evaluation | 1 day | Mon 16-12-12 | Mon 16-12-12 | **12** | | | | | | **-12** | | | |
| 38 |  | Writing scientific paper no. 1 | 5 days | Tue 16-12-13 | Mon 16-12-19 |  | | | | | |  | | | |
| 39 |  | Scientific convention/conference | 5 days | Tue 16-12-20 | Mon 16-12-26 |  | | | | | |  | | | |
| 40 |  | Holidays/Time off | 7 days | Tue 16-12-27 | Wed 17-01-04 |  | | | | | |  | | | |
|  | | | | | |  | | | |
| 41 |  |  |  |  |  |  | | | |
| 42 |  | **Session 4 Measurements (continued)** | **82 days** | **Thu 17-01-05** | **Fri 17-04-28** |  | | | |
| 43 |  | Chapter 2: Literature Review | 2 days | Thu 17-01-05 | Fri 17-01-06 |  | | | |
| 44 |  | Thesis writing | 10 days | Mon 17-01-09 | Fri 17-01-20 |  | | | |
| 45 |  | Data collection | 15 days | Mon 17-01-23 | Fri 17-02-10 |  | | | |
| 46 |  | Enrolment in ENR course | 1 day | Mon 17-02-13 | Mon 17-02-13 |  | | | |
| 47 |  | DGA 1033 | 20 days | Tue 17-02-14 | Mon 17-03-13 |  | | | |
| 48 |  | Presentation 4 and quarterly evaluation | 1 day | Mon 17-03-13 | Mon 17-03-13 | **03-13** | | | |
| 49 |  | Writing scientific paper no. 1 | 7 days | Tue 17-03-14 | Wed 17-03-22 |  | | | |
| 50 |  | Writing conference paper | 7 days | Thu 17-03-23 | Fri 17-03-31 |  | | | |
| 51 |  | Submitting scientific paper no. 1 | 1 day | Fri 17-03-31 | Fri 17-03-31 | **03-3** | | | |
| 52 |  | Submitting conference paper | 1 day | Fri 17-03-31 | Fri 17-03-31 | **03-3** | | | |
| 53 |  | Other (to be specified) | 10 days | Mon 17-04-03 | Fri 17-04-14 |  | | | |
| 54 |  | Holidays/Time off | 10 days | Mon 17-04-17 | Fri 17-04-28 |  | | | |
| 55 |  |  |  |  |  |  | | | |
| 56 |  | **Session 5 Modelling** | **88 days** | **Mon 17-05-01** | **Wed 17-08-30** |  | | | |
| 57 |  | Chapter 2: Literature Review | 2 days | Mon 17-05-01 | Tue 17-05-02 |  | | | |
| 58 |  | Thesis writing | 10 days | Wed 17-05-03 | Tue 17-05-16 |  | | | |
| 59 |  | Data collection (end) | 15 days | Wed 17-05-17 | Tue 17-06-06 |  | | | |
|  | | | Task | |  | |  | Idle summary | | | | |  |  |  |  |  |  |  |  |  |  |
|  | | | Splitting | |  | |  | Manual task | | | | |  |  |  |  |  |  |  |  |  |  |
|  | | | Milestone | |  | |  | Duration only | | | | |  |  |  |  |  |  |  |  |  |  |
| File: PhD\_2016-02-02\_timeline\_model  Date: Tue 22-08-09 | | | Summary  Project summary | |  | |  | Manual summary delay  Manual summary | | | | |  |  |  |  |  |  |  |  |  |  |
|  | | | External tasks | |  | |  | Start only | | | | |  |  |  |  |  |  |  |  |  |  |
|  | | | External milestones | |  | |  | End only | | | | |  |  |  |  |  |  |  |  |  |  |
|  | | | Idle task | |  | |  | Progress | | | | |  |  |  |  |  |  |  |  |  |  |
|  | | | Idle milestone | |  | |  | Due date | | | | |  |  |  |  |  |  |  |  |  |  |
| **Research Student :** Research Student Name | | |  | | Page 2 of 4 | |  |  | | | | |  |  |  |  |  |  |  |  |  |  |





|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Project:** Research Unit Logo Research Unit Name Project Title: | | | | | | | | | | | | | | | | | | | | | | |
| N° |  | Task | Duration | Start | End | D | 2016, Semester 1 | | | | | | 2016, Semester 2 | | | | | | 2017, Semester 3 | | | |
| J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A |
| 60 |  | Enrolment in XXX course | 1 day | Wed 17-06-07 | Wed 17-06-07 |  |  | | | | | |  | | | | | |  | | | |
| 61 |  | Digital modelling | 30 days | Thu 17-06-08 | Wed 17-07-19 |
| 62 |  | Presentation 5 and quarterly evaluation | 1 day | Wed 17-07-19 | Wed 17-07-19 |
| 63 |  | Writing scientific paper no. 2 | 10 days | Thu 17-07-20 | Wed 17-08-02 |
| 64 |  | Conference | 1 day | Wed 17-08-02 | Wed 17-08-02 |
| 65 |  | Other (to be specified) | 10 days | Thu 17-08-03 | Wed 17-08-16 |
| 66 |  | Holidays/Time off | 10 days | Thu 17-08-17 | Wed 17-08-30 |
| 67 |  |  |  |  |  |
| 68 |  | **Session 6 Modelling (continued)** | **83 days** | **Thu 17-08-31** | **Mon 17-12-25** |
| 69 |  | Chapter 2: Literature Review | 2 days | Thu 17-08-31 | Fri 17-09-01 |
| 70 |  | Thesis writing | 10 days | Mon 17-09-04 | Fri 17-09-15 |
| 71 |  | Enrolment in ENR810 course | 1 day | Mon 17-09-18 | Mon 17-09-18 |
| 72 |  | Digital modelling | 40 days | Tue 17-09-19 | Mon 17-11-13 |
| 73 |  | Presentation 6 and quarterly evaluation | 1 day | Mon 17-11-13 | Mon 17-11-13 |
| 74 |  | Writing scientific paper no. 2 | 10 days | Tue 17-11-14 | Mon 17-11-27 |
| 75 |  | Submitting scientific paper no. 2 | 1 day | Mon 17-11-27 | Mon 17-11-27 |
| 76 |  | Other (to be specified) | 10 days | Tue 17-11-28 | Mon 17-12-11 |
| 77 |  | Holidays/Time off | 10 days | Tue 17-12-12 | Mon 17-12-25 |
| 78 |  |  |  |  |  |
| 79 |  | **Session 7 Analysis/Summary** | **86 days** | **Tue 17-12-26** | **Tue 18-04-24** |
| 80 |  | Last tests/simulations | 10 days | Tue 17-12-26 | Mon 18-01-08 |
| 81 |  | Thesis writing | 15 days | Tue 18-01-09 | Mon 18-01-29 |
| 82 |  | Writing scientific paper no. 3 | 10 days | Tue 18-01-30 | Mon 18-02-12 |
| 83 |  | Data collection | 10 days | Tue 18-02-13 | Mon 18-02-26 |
| 84 |  | Enrolment in XXX course | 1 day | Tue 18-02-27 | Tue 18-02-27 |
| 85 |  | Analysis/summary/calculations | 20 days | Wed 18-02-28 | Tue 18-03-27 |
| 86 |  | Presentation 7 and quarterly evaluation | 1 day | Tue 18-03-27 | Tue 18-03-27 |
| 87 |  | Submitting scientific paper no. 3 | 1 day | Tue 18-03-27 | Tue 18-03-27 |
| 88 |  | Other (to be specified) | 10 days | Wed 18-03-28 | Tue 18-04-10 |
| 89 |  | Holidays/Time off | 10 days | Wed 18-04-11 | Tue 18-04-24 |
|  | | | Task | |  | |  | Idle summary | | | | |  |  |  |  |  |  |  |  |  |  |
|  | | | Splitting | |  | |  | Manual task | | | | |  |  |  |  |  |  |  |  |  |  |
|  | | | Milestone | |  | |  | Duration only | | | | |  |  |  |  |  |  |  |  |  |  |
| File: PhD\_2016-02-02\_timeline\_model  Date: Tue 22-08-09 | | | Summary  Project summary | |  | |  | Manual summary delay  Manual summary | | | | |  |  |  |  |  |  |  |  |  |  |
|  | | | External tasks | |  | |  | Start only | | | | |  |  |  |  |  |  |  |  |  |  |
|  | | | External milestones | |  | |  | End only | | | | |  |  |  |  |  |  |  |  |  |  |
|  | | | Idle task | |  | |  | Progress | | | | |  |  |  |  |  |  |  |  |  |  |
|  | | | Idle milestone | |  | |  | Due date | | | | |  |  |  |  |  |  |  |  |  |  |
| **Research Student :** Research Student Name | | |  | | Page 3 of 4 | |  |  | | | | |  |  |  |  |  |  |  |  |  |  |





|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Project:** Research Unit Logo Research Unit Name Projet Title: | | | | | | | | | | | | | | | | | | | | | | |
| N° |  | Task | Duration | Start | End | D | 2016, Semester 1 | | | | | | 2016, Semester 2 | | | | | | 2017, Semester 3 | | | |
| J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A |
| 90 |  |  |  |  |  |  |  | | | | | |  | | | | | |  | | | |
| 91 |  | **Session 8 Analysis/Summary** | **85 days** | **Wed 18-04-25** | **Tue 18-08-21** |
| 92 |  | Last tests/simulations | 10 days | Wed 18-04-25 | Tue 18-05-08 |
| 93 |  | Thesis writing | 15 days | Wed 18-05-09 | Tue 18-05-29 |
| 94 |  | Writing scientific paper no. 4 | 10 days | Wed 18-05-30 | Tue 18-06-12 |
| 95 |  | Data collection | 10 days | Wed 18-06-13 | Tue 18-06-26 |
| 96 |  | Analysis/summary/calculations | 20 days | Wed 18-06-27 | Tue 18-07-24 |
| 97 |  | Presentation 8 and quarterly evaluation | 1 day | Tue 18-07-24 | Tue 18-07-24 |
| 98 |  | Submitting scientific paper no. 4 | 1 day | Tue 18-07-24 | Tue 18-07-24 |
| 99 |  | Other (to be specified) | 10 days | Wed 18-07-25 | Tue 18-08-07 |
| 100 |  | Holidays/Time off | 10 days | Wed 18-08-08 | Tue 18-08-21 |
| 101 |  |  |  |  |  |
| 102 |  | **Session 9 Thesis Submission** | **82 days** | **Wed 18-08-22** | **Thu 18-12-13** |
| 103 |  | Thesis writing | 20 days | Wed 18-08-22 | Tue 18-09-18 |
| 104 |  | Conclusion | 5 days | Wed 18-09-19 | Tue 18-09-25 |
| 105 |  | Formatting appendices | 5 days | Wed 18-09-26 | Tue 18-10-02 |
| 106 |  | Initial Submission | 1 day | Wed 18-10-03 | Wed 18-10-03 |
| 107 |  | Writing scientific paper (if late or no. 5) | 10 days | Thu 18-10-04 | Wed 18-10-17 |
| 108 |  | Presentation 9 and quarterly evaluation | 1 day | Wed 18-10-17 | Wed 18-10-17 |
| 109 |  | Submitting scientific paper no. 4 | 1 day | Wed 18-10-17 | Wed 18-10-17 |
| 110 |  | Final Submission | 1 day | Thu 18-10-18 | Thu 18-10-18 |
| 111 |  | Thesis defence | 10 days | Fri 18-10-19 | Thu 18-11-01 |
| 112 |  | Scientific convention | 5 days | Fri 18-11-02 | Thu 18-11-08 |
| 113 |  | Other (to be specified) | 10 days | Fri 18-11-09 | Thu 18-11-22 |
| 114 |  | Thesis correction | 5 days | Fri 18-11-23 | Thu 18-11-29 |
| 115 |  | Holidays/Time off | 10 days | Fri 18-11-30 | Thu 18-12-13 |
|  | | | | | | | | | | | | | | | | | | | | | | |
|  | | | Task | |  | |  | Idle summary | | | | |  |  |  |  |  |  |  |  |  |  |
|  | | | Splitting | |  | |  | Manual task | | | | |  |  |  |  |  |  |  |  |  |  |
|  | | | Milestone | |  | |  | Duration only | | | | |  |  |  |  |  |  |  |  |  |  |
| File: PhD\_2016-02-02\_timeline\_model  Date: Tue 22-08-09 | | | Summary  Project summary | |  | |  | Manual summary delay  Manual summary | | | | |  |  |  |  |  |  |  |  |  |  |
|  | | | External tasks | |  | |  | Start only | | | | |  |  |  |  |  |  |  |  |  |  |
|  | | | External milestones | |  | |  | End only | | | | |  |  |  |  |  |  |  |  |  |  |
|  | | | Idle task | |  | |  | Progress | | | | |  |  |  |  |  |  |  |  |  |  |
|  | | | Idle milestone | |  | |  | Due date | | | | |  |  |  |  |  |  |  |  |  |  |
| **Research Student :** Research Student Name | | |  | | Page 4 of 4 | |  |  | | | | |  |  |  |  |  |  |  |  |  |  |



